PROJECT CHARTER

Hospital Appointment Optimization &

Patient Analytics System  (HAOPAS)

Version 1.0  |  June 2025

| Project Name | Hospital Appointment Optimization & Patient Analytics System (HAOPAS) |
| --- | --- |
| Project Sponsor | Hospital Director / Chief Operations Officer |
| Business Owner | OPD Head / Chief of Medicine |
| Project BA | Vaibhav Punde ¦ MBA Business Analytics |
| Version | 1.0 — Initial Charter |
| Date Prepared | June 2025 |
| Status | APPROVED |

# 1.  Executive Summary

City General Hospital (CGH) operates an Outpatient Department (OPD) serving an average of 1,200 patients per day across 14 specialties. Despite strong patient demand, the hospital consistently reports a no-show rate exceeding 30%, resulting in significant doctor idle time, revenue leakage, and patient dissatisfaction.

This project — HAOPAS — is initiated to conduct a structured Business Analysis of the appointment lifecycle, identify root causes of no-shows and scheduling inefficiencies, segment patients by risk profile, and deliver actionable KPI dashboards to guide operational and strategic decisions.

The deliverables of this project will equip the Hospital Director, OPD Head, and Scheduling Manager with data-driven insights to reduce no-shows by 15%, improve slot utilization by 20%, and enhance overall patient experience.

# 2.  Problem Statement

The following critical pain points have been identified across the OPD appointment lifecycle:

- No-Show Rate >30%: 3 in every 10 booked appointments result in no-shows — causing direct revenue loss and idle doctor time.

- Zero Predictive Capability: No mechanism exists to proactively identify high-risk patients who are likely to miss appointments.

- Manual Scheduling: Slot allocation is largely manual with no real-time utilization visibility.

- Inadequate Reminders: SMS reminders are inconsistent — sent to less than 60% of scheduled patients.

- No KPI Monitoring: The scheduling team operates without dashboards, making trend identification reactive rather than proactive.

- Underserved Waitlists: Cancelled and no-show slots are not systematically offered to waitlisted patients, compounding the revenue impact.

# 3.  Project Objectives

3.1  Primary Objectives

- Analyse 110,000+ appointment records to identify no-show patterns by age, neighbourhood, lead time, day, and chronic condition.

- Segment patients into High / Medium / Low no-show risk tiers to enable targeted intervention.

- Develop executive KPI dashboards in Power BI (primary) and Tableau (secondary) for real-time monitoring.

- Perform Root Cause Analysis (RCA) and Gap Analysis to identify process improvement opportunities.

- Produce a complete BRD, FRD, and Agile User Story backlog for the proposed scheduling analytics solution.

3.2  SMART Objectives

| Objective | Target | Measurement |
| --- | --- | --- |
| Reduce no-show rate | ↓ 15% | Monthly no-show % report |
| Improve slot utilization | ↑ 20% | Doctor utilization dashboard |
| SMS reminder coverage | 100% of bookings | Reminder log report |
| Dashboard go-live | Within 4 weeks | UAT sign-off date |
| Patient segmentation model | 3 risk tiers active | Segmentation output file |

# 4.  Project Scope

| IN SCOPE | OUT OF SCOPE |
| --- | --- |
| - OPD (Outpatient) appointment analysis - No-show prediction & patient segmentation - KPI dashboards (Power BI & Tableau) - BRD, FRD, User Stories documentation - Gap Analysis & Root Cause Analysis - SQL-based data analysis & Python cleaning - UAT plan, test cases, and sign-off | - Inpatient & Emergency department operations - Real-time system integration or API development - EHR/EMR system changes or implementation - Financial billing or insurance claims processing - ML model deployment to production - HIPAA/compliance implementation |

# 5.  KPIs & Success Metrics

| # | KPI | Current Baseline | Target | Reporting Frequency |
| --- | --- | --- | --- | --- |
| 1 | No-Show Rate | >30% | <15% | Monthly |
| 2 | Doctor Slot Utilization % | ~65% | >85% | Weekly |
| 3 | SMS Reminder Coverage % | <60% | 100% | Daily |
| 4 | Average Appointment Lead Time (days) | Unknown | Tracked & segmented | Monthly |
| 5 | High-Risk Patient Identification Rate | 0% (none) | >90% of flagged cases | Weekly |
| 6 | Dashboard Adoption (active users) | 0 | 5+ stakeholders | Post go-live |

# 6.  Assumptions & Constraints

| ASSUMPTIONS | CONSTRAINTS |
| --- | --- |
| - Dataset used is the Kaggle 'Medical Appointment No Show' dataset (~110K records) - Data is treated as real hospital data for analysis purposes - Stakeholders and hospital names used are fictionalised - All tools used are free/open-source versions - Project team consists of a single BA (Vaibhav Punde) | - Project duration: 4 weeks maximum - No budget allocated — free tools only (Power BI Desktop, Tableau Public, Jira Free) - No real patient PHI/PII — anonymised data only - No production system integration or live data pipeline - Scope limited to OPD appointments; inpatient excluded |

# 7.  High-Level Project Timeline

| Week | Phase | Key Deliverables | Owner | Status |
| --- | --- | --- | --- | --- |
| 1 | Phases 1–5: Initiation & Requirements | Project Charter, Stakeholder Register, BRD, FRD, Jira Board | Vaibhav Punde | In Progress |
| 2 | Phases 6–8: Data & SQL Analysis | Data Dictionary, Cleaned Dataset (Python), SQL Query Bank | Vaibhav Punde | Planned |
| 3 | Phases 9–11: Analytics & Dashboards | Patient Segmentation Model, Power BI Dashboard, Tableau View | Vaibhav Punde | Planned |
| 4 | Phases 12–14: UAT & Portfolio | UAT Test Cases, Sign-off Sheet, GitHub Repo, LinkedIn Post | Vaibhav Punde | Planned |

# 8.  Key Stakeholders

| Stakeholder | Role | Interest | Influence | Engagement |
| --- | --- | --- | --- | --- |
| Hospital Director | Project Sponsor | Revenue impact & strategic KPIs | HIGH | Inform |
| OPD Head | Business Owner | Doctor utilization & OPD efficiency | HIGH | Consult |
| Scheduling Manager | Process Owner | Slot management & no-show reduction | MEDIUM | Collaborate |
| IT Manager | Technical Lead | Dashboard specs & data integration | MEDIUM | Consult |
| Patients (End Users) | Beneficiaries | Easier scheduling & reminders | LOW | Monitor |

# 9.  Risk Register

| # | Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Dataset does not fully represent real OPD patterns | Medium | Medium | Clearly document dataset source and limitations in BRD |
| R2 | Scope creep into inpatient or clinical analytics | Low | High | Strict scope boundary enforced via Charter sign-off |
| R3 | Power BI or Tableau skill gaps causing dashboard delays | Low | Medium | Use existing dashboard as reference; time-box dashboard work to 5 days |
| R4 | Timeline overrun due to documentation volume | Medium | Medium | Use templates and weekly milestone tracking via Jira |

# 10.  Charter Sign-Off

By signing below, the stakeholders acknowledge that they have reviewed and approved this Project Charter and authorise the project to proceed to Phase 2.

| Name & Role | Signature | Date | Comments |
| --- | --- | --- | --- |
| Hospital Director (Project Sponsor) |  | __ / __ / 2025 |  |
| OPD Head (Business Owner) |  | __ / __ / 2025 |  |
| IT Manager (Technical Lead) |  | __ / __ / 2025 |  |
| Vaibhav Punde (Business Analyst) |  | 28 / 06 / 2025 |  |

HAOPAS Project Charter  |  Prepared by Vaibhav Punde  |  MBA Business Analytics  |  Version 1.0  |  June 2025